## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | ACS |  | Progress Classes: | Ahead
Group Member: | Aili Gong |  |  | On-track
Group Member: | Catherine Thomas |  |  | Behind
Group Member: | Sam Mellor |  |  | Way Behind
Tutor: | Tim
Class: | Friday 1430
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Aili Gong | Catherine Thomas | Sam Mellor
| Finished |  | Group Formed |  | Weekly Contribution | Implemented basic menu; discussed data types | Discussed data types | Group setup admin; discussed data types
| In Progress |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
Basic Main menu with "credits"
Choice of where to use linked list, vector & array
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Aili Gong | Catherine Thomas | Sam Mellor
|  |  | Initial Design of ADTs (classes and potential methods) |  | Weekly Contribution | Implemented models / ADTs for gameplay | Implemented main menu and user prompt | Implemented models for game history
|  |  | Main menu |  | Issues
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Other Notes
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Aili Gong | Catherine Thomas | Sam Mellor
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Aili Gong | Catherine Thomas | Catherine Thomas
|  |  | Fully complete implementation and error free |  | Weekly Contribution
|  |  | Full error checking of user prompt |  | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind